## Government Printing Department
GOVERNMENT PRINTING DEPARTMENT
PROCUREMENT PLAN FOR 2021 FY
PREPARED BY THE PROCUREMENT UNIT
APPROVED BY THE PROCUREMENT COMMITTEE

## Summary
Government Printing Department |  |  |  | SUMMARY OF 2021 PROCUREMENT PLAN
PROCUREMENT CATEGORY | Number of restricted type | Number of open type |  | VALUES
|  | NCB | ICB | Total value of restricted type (Le) | Total value of unrestricted type NCB (Le) | Total value of unrestricted type ICB (Le) | Total value of open (Le) | Total value of open and restricted type (Le) | Remarks
GOODS | 2 | 3 | 0 | 109900000 | 994000000 | 0 | 994000000 | 1103900000
WORKS | 1 | 1 | 0 | 120000000 | 800000000 | 0 | 800000000 | 920000000
SERVICES | 3 | 0 | 0 | 211200000 | 0 | 0 | 0 | 211200000
TOTAL | 6 | 4 | 0 | 441100000 | 1794000000 | 0 | 1794000000 | 2235100000
Summary of Procurement and Non-Procurement Items
Procurement Related Items | Total Restricted Bidding | 441100000
| Total Open Competitive Bidding | 1794000000
Sub Total |  | 2235100000
Non-Procurement Related Items |  | 1192605000
Total Operational Budget |  | 3427705000

## GOODS
GOODS 2021 FY
Name of Procuring Entity: Government Printing Department
Name of Sub-Department:Administration
Source of Funding: GOVERNMENT OF SIERRA LEONE
[6 empty] | BASIC DATA |  |  | Specs & bills of quantities & Bid Document |  | Bidding period |  | Bid Evaluation |  |  |  | Contract Implementation
Contract Package Number | Description of items | procurement number | plan vs actual dates | lot number | Qty | Estimated Cost. Le | Procurement Method | Preparation and Submission of Bidding Document by Procurement Unit | date of clearance by Procurement Committee | Choice of Newspapers for advert publication | Bid Invitation date (advert) | Bid closing/opening date | Submission of evaluation report | Approval by Procurement Committee | Date of Contract Award /Notification of award | Date of Contract Signature | Intial Payment Opening of letter of credit | Delivery | Inspection& final accptance | Remarks
PRSP/Ref: | Duration of procurement process
| Computer Stationery (Q1) | N.PA (ADMIN.) 2007 | Plan |  |  | 126 M | NCB |  | 13/11/2006 |  | 20/11/2006 | 2006-12-18 | 2007-01-03 | 2007-01-10 | 2007-01-17 | 2007-01-31 | 2007-02-14 | 2007-02-28
Actual
| Computer Stationery (Q2) | N.PA (ADMIN.) 2007 | Plan |  |  | 126 M | NCB |  | 2007-01-30 |  | 06.02.07 | 2007-03-06 | 2007-03-20 | 2007-03-27 | 2007-04-03 | 2007-04-17 | 01/05/07 | 2007-05-15
Actual
| Computer Stationery (Q3) | N.PA (ADMIN.) 2007 | Plan |  |  | 126 M | NCB |  | 2007-04-18 |  | 2007-04-26 | 2007-05-29 | 2007-06-12 | 19/06.07 | 2007-06-26 | 2007-07-10 | 2007-07-24 | 2007-08-07
Actual
| Computer Stationery (Q4) | N.PA (ADMIN.) 2007 | Plan |  |  | 126 M | NCB |  | 2007-05-10 |  | 2007-07-30 | 2007-08-30 | 2007-09-20 | 2007-09-27 | 2007-10-04 | 2007-10-18 | 2007-11-01 | 2007-11-15
Actual
| Stationery (Q1) | N.PA (ADMIN.) 2007 | Plan |  |  | 90 M | NCB |  | 2006-07-11 |  | 14/11/2006 | 21/11/2006 | 19/12/2006 | 26/12/2006 | 2007-01-11 | 2007-08-01 | N/A | 15/1/2007
Actual
| Stationery (Q2) | N.PA (ADMIN.) | Plan |  |  | 90 M | NCB |  | 2007-12-04 |  | 19/4/2007 | 20/4/2007 | 18/5/2007 | 25/5/2007 | 2007-01-06 | 2007-08-06 | N/A | 15/6/2007
Actual
| Stationery (Q3) | N.PA (ADMIN.) | Plan |  |  | 90 M | NCB |  | 2007-06-09 |  | 13/9/2007 | 20/9/2007 | 18/10/2007 | 25/10/2007 | 2007-01-06 | 2007-08-11 | N/A | 15/11/2007
Actual
| Stationery (Q4) | N.PA (ADMIN.) | Plan |  |  | 90 M | NCB |  | 17/10/2007 |  | 24/10/2007 | 30/11/2007 | 30/11/2007 | 2007-07-12 | 14/12/2007 | 21/12/2007 | N/A | 28/12/2007
Actual
| Uniforms & Prot. Clothing | N.PA (ADMIN.) | Plan |  |  | 120 M | NCB |  | 2006-08-11 |  | 15/11/2006 | 22/11/2006 | 20/12/2006 | 27/12/2006 | 2007-02-01 | 2007-08-01 | N/A | 15/1/2007
Actual
| Printing | N.PA (ADMIN.) | Plan |  |  | 9.06 | NCB |  | 2006-08-12 |  | Nil | 13/12/2006 | 27/12/2006 | 2007-02-01 | 2007-06-01 | 13/1/2007 | N/A | 20/1/2007
Actual
| Training Materials | N.PA (ADMIN.) | Plan |  |  | 60 M | RFQ |  | 2006-08-12 |  | Nil | 13/12/2006 | 27/12/2006 | 2007-02-01 | 6/12007 | 13/1/2007 | N/A | 2007-02-10
Actual
| Cleaning Materials | N.PA (ADMIN.) | Plan |  |  | 117600 | RFQ |  | 2006-12-21 |  | 2006-12-28 | 2007-01-11 | 2007-01-18 | 2007-01-25 | 2007-02-01 | 2007-02-08 | N/A | 2007-02-15
Actual
| Security Consulting | N.PA (ADMIN.) | Plan |  |  | 60 M | NCB |  | 15/12/2007 |  | Nil | 22/12/2007 | 2007-05-01 | 2007-12-01 | 16/12007 | 23/1/2007 | N/A | 30/1/2007
Actual
| Medical Expenses | N.PA (ADMIN.) | Plan |  |  | 264 M | RFQ |  | 2006-04-11 |  | 2006-11-11 | 18/11/2006 | 2006-06-12 | 23/12/2006 | 30/12/2006 | 2007-07-01 | N/A | 2007-12-01
Actual
| Hire of Transport | N.PA (ADMIN.) | Plan |  |  | 336 M | NCB |  | 21/11/2006 |  | 28/11/2006 | 2006-05-12 | 2007-02-01 | 2007-09-01 | 16/1/2007 | 23/1/207 | N/A | 30/1/2007
Actual
| Prepaymet Meter | N.PA (ADMIN.) | Plan |  |  | 8.795 M | ICB |  | 2006-12-15 |  | 2006-12-22 | 2007-02-05 | 2007-02-19 | 2007-03-05 | 2007-03-19 | 2007-04-02 | 2007-04-15 | 2007-05-15
Actual
| Building | N.PA (ADMIN.) | Plan |  |  | 482,500,00 | ICB |  | 27/9/2006 |  | 2006-11-10 | 18/10/2006 | 29/11/2006 | 13/12/2006 | 27/12/2006 | 2007-03-01 | 17/1/2007 | 31/1/2007
Actual
| Gen. Plant & Equipment | NPA/ Gen. | Plan |  |  | 606195267 | ICB |  | 2006-11-09 |  | 25/9/2006 | 2006-02-10 | 13/11/2006 | 27/1/2006 | 2006-11-12 | 18/12/2006 | 2007-01-01 | 15/1/2007
Actual
| Dist. System | NPA/Dist | Plan |  |  | 412030625 | ICB |  | 30/8/2006 |  | 13/9/2006 | 20/9/2006 | 30/10/2006 | 13/11/2006 | 27/11/2006 | 2006-04-12 | 18/12/2006 | 2007-01-01
Actual
1 | STATIONERY | GPD/OGP/NCB/01/2021 | PLAN | 1 | various | 180000000 | NCB | 2020-10-05 | 2020-10-26 | 2020-10-26 | 2020-10-26 | 2019-11-28 | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2020-12-30 | 2021-01-04 | 2021-01-11 | 2021-02-03 | Framework Contract
ACTUAL
2 | COMPUTER RUNNING COST | GPD/OGP/NCB/02/2021 | PLAN | 1 | various | 634000000 | NCB | 2020-10-12 | 2020-10-19 | 2020-10-19 | 2020-10-19 | 2020-11-19 | 2020-11-26 | 2020-12-03 | 2020-12-10 | 2020-12-23 | 2020-12-28 | 2021-01-07 | 2021-02-05
ACTUAL
3 | COMPUTER DESKTOPS | GPD/OGP/RFQ/01/2021 | PLAN | 1 | various | 70000000 | RFQ | 2020-10-13 | 2020-10-13 | NA | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-09 | 2020-11-30 | N/A | 2020-12-14 | 2020-12-14 | Framework Contract
ACTUAL
4 | OFFICE SUNDRIES | GPD/OGP/NCB/03/2021 | PLAN | 1 | various | 180000000 | NCB | 2020-10-15 | 2020-10-29 | 2020-10-29 | 2020-10-29 | 2020-11-30 | 2020-12-02 | 2020-12-09 | 2020-12-14 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-02-03
ACTUAL
5 | UNIFORM/PROTECTIVE CLOTHING | GPD/OGP/RFQ/02/2021 | PLAN | 1 | various | 39900000 | RFQ | 2020-11-16 | 2020-11-16 | NA | 2020-11-18 | 2020-11-25 | 2020-12-02 | 2020-12-09 | 2020-12-09 | 2020-12-23 | N/A | 2021-01-06 | 2021-01-06
|  |  | ACTUAL |  |  | 1103900000
Signature of Chairman: Signature of Procurement Officer:
Name: Name:

## WORKS
WORKS 2021
Name of Procuring Entity: GOVERNMENT PRINTING DEPARTMENT
Name of Sub-Department: ADMINISTRATION
Source of funding: GOVERNMENT OF SIERRA LEONE
|  |  |  | BASIC DATA |  |  | Drafting of bid documents, | specs & bills of quantities | Notice of advert | Bidding period |  | Bid Evaluation |  |  |  | Contract Implementation
| Description of works | procurement number | lot number | estimated cost. Le | procurement method | plan vs actual dates | preparation & submission by procurement unit | date of clearance by Procurement Committee | dates & names of local newspapers | Bid Invitation date | Bid closing/opening date | Submission of evaluation report | Approval by Procurement Committee | Date of Award | Date of Contract signature | Date of mobilisation | Contract Execution | Defect Liability period
1 | Ugrade & Rehabilitation of Government Printing Bookshop | GPD-WRK/OGP/NCB/01/2021 |  | 800000000 | NCB | Plan | 2020-10-26 | 2020-10-26 | 2020-10-26 | 2019-11-27 | 2020-12-18 | 2020-12-28 | 2020-12-30 | 2021-01-14 | 2021-01-28 | 2021-02-26 | 2021-03-01
Actual
2 | Building Maintenance at GPD | GPD-WRK/OGP/RFQ/02/2021 |  | 120000000 | RFQ | Plan | 2020-10-05 | 2020-10-05 | NA | 2020-10-26 | 2019-11-28 | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2020-12-30 | N/A | 2021-01-20 | 2021-02-22
Actual
920000000
Signature of Chairman: Signature of Procurement Officer:
Name: Name:

## SERVICES
NON CONSULTANCY SERVICES 2021
Name of Procuring Entity: GOVERNMENT PRINTING DEPARTMENT
Name of Sub-Department: ADMINISTRATION
Source of funding: GOVERNMENT OF SIERRA LEONE
|  |  |  | BASIC DATA |  |  | Contract Type |  | Expression of Interest (Where necessary) |  |  | RFP Preparation |  | Consultants' Proposals | Consultants' Proposals |  | Proposal Evaluation(Technical and Financial) | [5 empty] | Negotiations |  |  | Contract Finalisation |  |  | Contract Implementation
| Description of consultancy | procurement number | consulting category | estimated cost. Le | estimated cost.USD | selection method | Lumpsum or Time-Based | plan vs actual dates | EOI invited | Shortlist | Date of clearance by Procurement Committee | Preparation of RFP | Date of approval by Procurement Committee | Invitation Date | Submission Date/Opening | Submission of Evaluation Report (T) | Approval of Evaluation Report(T) | Opening of Financial Proposal | Submission of combined evaluation report(T&F) | Approval of Evaluation Report(T&F) | plan vs actual dates | Negotiations | Draft Contract | Approval of Negotiation Report | Contract Amount | Date of Award | Date of Contract signature | Mobilisation/ Advance payment | Inception report | Draft report | Final report | Final cost
1 | ICT Infrasture Development | GPD-SER/OGP/RFQ/01/2021 |  | 94200000 | N/A | L C S | Lumpsum | Plan | N/A | N/A | 2020-10-05 | 2020-10-08 | 2020-11-09 | 2021-11-16 | 2021-11-23 | N/A | NA | NA | 2020-12-07 | 2020-12-14 | Plan | NA | 2019-12-20 | NA | 18000000 | 2020-12-21 | 2021-01-04 | N/A | NA | NA | Quarterly
Actual
2 | Generator Running Cost (Maintenance) | GPD-SER/OGP/RFQ/02/2021 |  | 65000000 | N/A | L C S | Lumpsum | Plan | N/A | N/A | 2020-12-03 | 2020-12-17 | 2020-12-24 | 2020-12-28 | 2021-01-22 | 2021-01-29 | 2021-02-08 | 2021-02-15 | 2021-02-21 | 2021-02-28 | Plan | NA | 2021-03-07 | NA | 1664000000 | 2021-03-14 | 2021-03-29 | N/A | NA | NA | Quarterly
[8 empty] | Actual | [12 empty] | Actual
3 | Vehicle & Equipment Running Cost (Maintenance) | GPD-SER/OGP/NCB/03/2021 |  | 52000000 | N/A | L C S | Lumpsum | Plan | N/A | N/A | 2020-12-03 | 2020-12-17 | 2020-12-24 | 2020-12-28 | 2021-01-22 | 2021-01-29 | 2021-02-08 | 2021-02-15 | 2021-02-21 | 2021-02-28 | Plan | NA | 2021-03-07 | NA | 1664000000 | 2021-03-14 | 2021-03-29 | N/A | NA | NA | Quarterly
|  |  |  | 211200000 |  |  |  | Actual | [12 empty] | Actual
Signature of Chairman: Signature of Procurement Officer:
Name: Name:

## PDF & NPDF
GOVERNMENT PRINTING DEPARTMENT
Disbursement Forecast For 2021 Budget
Contract Package Number | Contract Description | Procurement Method | Contract Value [ Le] | Payments To Date Le | Quarter 1 (Jan - Mar) Le | Quarter 2 (Apr - Jun ) Le | Quarter 3 (Jul - Sep) Le | Quarter 4 (Oct - Dec) Le | Rollover Le
GOODS
1 | STATIONERY | NCB | 180000000 |  | 45000000 | 45000000 | 45000000 | 45000000 | 0
2 | COMPUTER RUNNING COST | NCB | 634000000 |  | 158500000 | 158500000 | 158500000 | 158500000 | 0
3 | COMPUTER DESKTOPS | RFQ | 70000000 |  | 17500000 | 17500000 | 17500000 | 17500000 | 0
4 | OFFICE SUNDRIES | NCB | 180000000 |  | 45000000 | 45000000 | 45000000 | 45000000 | 0
5 | UNIFORM/PROTECTIVE CLOTHING | RFQ | 39900000 |  | 9975000 | 9975000 | 9975000 | 9975000 | 0
|  | SUBTOTAL | 1103900000 |  | 275975000 | 275975000 | 275975000 | 275975000 | 0
WORKS
| UPGRADE & REHABILITATION OF GOVERNMENT PRINTING BOOKSHOP | NCB | 800000000 |  | 200000000 | 200000000 | 200000000 | 200000000 | 0
1 | BUILDING MAINTENANCE | RFQ | 120000000 |  | 120000000 |  |  |  | 0
|  | SUBTOTAL | 920000000 |  | 320000000 | 200000000 | 200000000 | 200000000 | 0
SERVICES
1 | ICT INFRASTURE DEVELOPMENT | RFQ | 94200000 |  | 23550000 | 23550000 | 23550000 | 23550000 | 0
2 | GENERATOR RUNNING COST | RFQ | 65000000 |  | 16250000 | 16250000 | 16250000 | 16250000 | 0
3 | VEHICLE & EQUIPMENT RUNNING COST | RFQ | 52000000 |  | 13000000 | 13000000 | 13000000 | 13000000 | 0
|  | SUBTOTAL | 211200000 |  | 52800000 | 52800000 | 52800000 | 52800000
| Total (PDF) |  | 2235100000
NON PROCUREMENT DISBURSEMENT FORECAST
Serial Number | Contract Description | Procurement Method | Amount Le | Payments To Date Le | Quarter 1 Jan - Mar Le | Quarter 2 Apr - Jun Le | Quarter 3 Jul - Sep Le | Quarter 4 Oct - Dec Le | Rollover Le
STANDARD ITEMS
1 | Electricity Supply | N/A | 900000000 |  | 225000000 | 225000000 | 225000000 | 225000000 | 0
2 | Water Supply | N/A | 12000000 |  | 3000000 | 3000000 | 3000000 | 3000000 | 0
3 | Official Reception, Ent. & Hospitality | N/A | 50000000 |  | 12500000 | 12500000 | 12500000 | 12500000 | 0
4 | Contigience | N/A | 14000000 |  | 3500000 | 3500000 | 3500000 | 3500000 | 0
5 | Imprest | N/A | 48000000 |  | 12000000 | 12000000 | 12000000 | 12000000 | 0
6 | Vehicle Hire | N/A | 75600000 |  | 18900000 | 18900000 | 18900000 | 18900000 | 0
7 | Technical Training for Staffs | N/A | 92005000 |  | 23001250 | 23001250 | 23001250 | 23001250 | 0
|  | SUB TOTAL | 1191605000 |  | 297901250 | 297901250 | 297901250 | 297901250
NON STANDARD ITEMS
1 | Insurance & License | N/A | 1000000 |  | 1000000
|  | SUB TOTAL | 1000000
| Total (NPDF) |  | 1192605000
| Total (PDF + NPDF) |  | 3427705000
Signature of Chairman: Signature of Procurement Officer:
Name: Name: