## Goods
6
GOODS
`
Name of Sub-Department: ADMINISTRATION AND TECHNICAL
Source of funding: GOSL
| Financial Year | 2021
Serial No. | Description of items | Procurement No. | lot No. | Qty. | Estimated cost. (Le 000) | Procurement Method | Plan vs Actual Dates | Preparation and Submission by Procurement Unit 1wk | Clearance by the Procuremnet Committee 1wk max | Date and Local Newspapers (No Time) | Bid Invitation Date | Bid Closing Date | Submission of Evaluation Report 1wk | Approvals by Procurement Committee (3-4 days) | Date of Award 1 wk | Date of Contract Signature (1 wk max) | Date of Opening Letter of Credit/ Advance Payment for works (0 days) | Arrival of Goods/ Execution Period (1wk - 3mnths) | Inspection & Final Acceptance (I day)
1 | Stationery | MFMR/ADMIN/NCB/01/2021 | 1 | Various | 420000 | NCB | Plan | 2020-12-07 | 2020-12-14 | 2020-12-15 | 2020-12-15 | 2021-01-12 | 2021-01-19 | 2021-01-22 | 2021-01-29 | 2021-02-05 | 2021-02-08 | 2021-02-15 | 2021-02-16
Actual
2 | Computer Consumables | MFMR/ADMIN/NCB/02/2021 | 1 | Various | 300000 | NCB | Plan | 2020-11-23 | 2020-11-30 | 2020-12-01 | 2020-12-01 | 2020-12-29 | 2021-01-05 | 2021-01-08 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-05 | 2021-02-08
Actual
3 | Computers and Accessories | MFMR/ADMIN/NCB/03/2021 | 1 | Various | 465500 | NCB | Plan | 2020-12-01 | 2020-12-08 | 2020-12-09 | 2020-12-09 | 06/01/2020 | 2021-01-13 | 2020-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-16
Actual
4 | Office Furniture & Equipment | MFMR/ADMIN/NCB/04/2021 | 1 | Various | 786600 | NCB | Plan | 2020-12-09 | 2020-12-16 | 2020-12-17 | 2020-12-17 | 2021-01-14 | 2020-12-28 | 2020-12-31 | 2021-01-07 | 2021-01-14 | 2021-01-21 | 2021-02-18 | 2021-02-19
Actual
5 | Motor Bike and Number plates | MFMR/ADMIN/NCB/05/2021 | 1 | Various | 325000 | NCB | Plan | 2020-01-04 | 2021-01-11 | 2021-01-12 | 2021-01-12 | 2021-02-09 | 2021-02-16 | 2021-02-19 | 2021-02-26 | 2021-03-05 | 2021-05-12 | 2021-07-05 | 2021-07-06
Actual
6 | Boats and Outboard Engines | MFMR/ADMIN/NCB/06/2021 | 1 | Various | 1404000 | NCB | Plan | 2020-12-14 | 2020-12-21 | 2020-12-22 | 2020-12-22 | 2021-01-19 | 2021-01-26 | 2021-01-29 | 2021-02-05 | 2021-02-12 | 2021-02-15 | 2021-03-15 | 2021-03-16
Actual
7 | Fishing Nets and Gears | MFMR/ADMIN/ICB/01/2021 | 1 | Various | 5805719 | ICB | Plan | 2021-01-06 | 2021-01-13 | 2021-01-14 | 2021-01-14 | 2021-02-25 | 2021-03-01 | 2021-03-04 | 2021-03-11 | 2021-03-18 | 2021-03-25 | 2021-05-13 | 2021-05-14
Actual
8 | Vehicles and Motorbikes | MFMR/ADMIN/NCB/02/2021 | 1 | Various | 235 | NCB | Plan | 2021-02-03 | 2021-02-10 | 2021-02-11 |  | 11/02/2021 -11/03/2021 | 2021-03-18 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-05-24 | 2021-05-25
Actual
9 | Raw Materials for Formulation of Fish Food | MFMR/ADMIN/NCB/07/2021 | 1 | Various | 301500 | NCB | Plan | 2020-12-15 | 2020-12-22 | 2020-12-28 | 2020-12-28 | 2021-01-25 | 2021-02-01 | 2021-02-05 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-26 | 2021-03-29
Actual
10 | Tools for landing sites cleaning: | MFMR/ADMIN/NCB/08/2021 | 1 | Various | 197600 | NCB | Plan | 2020-12-21 | 2020-12-28 | 2020-12-29 | 2020-12-29 | 2021-01-26 | 2021-02-02 | 2021-02-05 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-26 | 2021-03-29
Actual
11 | 0 | ,. | 1 | various | 5812540 | ICB | Plan | 2020-12-15 | 2020-12-22 | 2020-12-23 | 2020-12-23 | 2021-01-20 | 372941 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-22 | 2021-03-23
Actual
12 | Provisions and Sundries | MFMR/ADMIN/NCB/09/2021 | 1 | Various | 232000 | NCB | Plan | 2020-12-23 | 2020-12-30 | 2020-12-31 | 2020-12-31 | 2020-01-28 | 2021-02-04 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-09
Actual
13 | Staff Uniforms; | MFMR/ADMIN/NCB/10/2021 | 1 | Various | 144000 | NCB | Plan | 2020-12-15 | 2020-12-22 | 2020-12-23 | 2021-01-06 | 25/01/2021 | 2021-02-01 | 2021-02-04 | 2021-02-11 | 2021-02-18 | 2021-02-25 | 2021-03-11 | 2021-03-12
Actual
14 | Lubricant for JMC Generator | MFMR/ADMIN/RFQ/01/2021 | 1 | Various | 2600 | RFQ | Plan | 2021-01-04 | 2021-01-11 | N/A | 2021-01-12 | 2021-01-26 | 2021-01-29 | 2021-02-02 | 2021-02-09 | 2021-02-16 | N/A | 2021-02-19 | 2021-02-22
Actual
15 | Measuring guages | MFMR/ADMIN/NCB/11/2021 | 1 | Various | 221000 | NCB | Plan | 2021-01-11 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-02-17 | 2021-02-24 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-04-26 | 2021-04-28
Actual
16 | Procurement of laboratory tools and reagents | MFMR/ADMIN/NCB/12/2021 | 1 | Various | 550000 | NCB | Plan | 2020-12-28 | 2021-01-04 | 2021-01-05 | 2021-01-05 | 2021-02-02 | 2021-02-09 | 2021-02-12 | 2021-02-19 | 2021-03-05 | 2021-03-19 | 2021-04-16 | 2021-04-19
Actual
17 | Procurement of the two fish feed machines | MFMR/ADMIN/NCB/13/2021 | 1 | Various | 345000 | NCB | Plan | 2021-01-06 | 2021-01-13 | 2021-01-14 | 2021-01-14 | 2021-02-11 | 2021-02-18 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-29 | 2021-04-26 | 2021-04-27
Actual
18 | Oil Paints, Paint brush and Thinner | MFMR/ADMIN/RFQ/02/2021 | 1 | Various | 70000 | RFQ | Plan | 2021-01-04 | 2021-01-11 | N/A | 2021-01-12 | 2021-01-26 | 2021-01-29 | 2021-02-02 | 2021-02-09 | 2021-02-16 | N/A | 2021-02-19 | 2021-02-22
Actual
19 | Fish, Safety and Rain Gears | MFMR/ADMIN/NCB/14/2021 | 1 | Various | 2204750 | NCB | Plan | 2020-12-07 | 2020-12-14 | 2020-12-15 | 2020-12-15 | 2021-01-12 | 2021-01-19 | 2021-01-22 | 2021-01-29 | 2021-02-05 | 2021-02-08 | 2021-02-15 | 2021-02-16
Actual
| Total Cost |  |  |  | 19588044
Date of Approval by Procurement Committee…………...……………………………
Signature of Chairman, Procurement Committee…………………………………….
Prepared By: John Foray Lamin:…………………………………………..

## Works
WORKS
Name of Procuring Entity: MINISTRY OF FISHERIES AND MARINE RESOURCES
Name of Sub-Department: ADMINISTRATION AND TECHNICAL
Source of funding:___________GOSL_________________
[7 empty] | Preparation of technical information & bid documents | Review of documents | Notice of advert | Bidding period |  | Bid Evaluation |  |  |  | Contract Implementation
| Description of works | Proc. No. | Lot No. | estimated cost in Leones | procurement method | plan vs actual dates | Preparation and Submission by Procurement Unit 1wk | Clearance by the Procuremnet Committee 1wk max | Date and Local Newspapers (No Time) | Bid Invitation To Bid Closing / Opening 2 wks | Submission of Evaluation Report 1wk | Approvals by Procurement Committee (3-4 days) | Date of Award 1 wk | Date of Contract Signature (1 wk max) | Date of Opening Letter of Credit/ Advance Payment for works (0 days) | Arrival of Goods/ Execution Period (1wk - 3mnths) | Inspection & Final Acceptance (I day)
1 | Construction of standard 5-10 boat for experimental fishing | MFMR/AQC/CW/RFQ/01/2021 |  | 150000000 | RFQ | Plan | 2021-01-04 | 2021-01-11 | 2021-01-12 | 12/01/2021 -01/02/2021 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-15 | 2021-03-29 | 2021-05-24 | 2021-05-31
Actual
2 | Rehabilitation of Outstation Kissy Outstation | MFMR/AQC/CW/NCB/01/2021 |  | 1500000000 | NCB | Plan | 2021-01-25 | 2021-02-01 | 2021-02-02 | 02/02/2021 -01/03.2021 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-07-12 | 2021-07-19
Actual
4 | Extension of LAN Network Infrastructor | MFMR/AQC/CW/NCB/02/2021 |  | 237500000 | NCB | Plan | 2021-02-01 | 2021-02-08 | 2021-02-09 | 09/02/2021 -09/03/2021 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-20 | 2021-05-18 | 2021-05-25
Actual
5 | Building Maintenance | MFMR/AQC/CW/RFQ/02/2021 |  | 170000000 | RFQ | Plan | 2021-01-18 | 2021-01-25 | 2021-01-26 | 26/01/2021 -23/02/2021 | 2021-03-02 | 2021-03-09 | 2023-03-16 | 2021-03-23 | 2021-04-20 | 2021-05-18 | 2021-05-25
Actual
| Total Cost |  |  | 2057500000
Signature of Chairman, Procurement Committee…………………………………….
Prepared By: John Foray Lamin:………………………………..

## Services
SERVICES
Name of Sub-Department: ADMINISTRATION AND TECHNICAL
|  |  |  | Financial Year |  | 2021
Source of funding: GOSL
|  |  | BASIC DATA |  | Drafting of bid documents, | specs & Bills of Quantities |  | Bidding period | Bid Evaluation
Serial N0. | Description of consultancy | procurement number | estimated cost. Le | selection method | plan vs actual dates | Prepare and advertise Expreson of Interest (EOI) 1wk | Receive Application(s)4 wks | Short-list Consultants 1 wk | Prepare Terms of Reference (TOR) and Request for Proposal (RFP) 2wks | Reviewand Approval 2wks | Invite Proposals4wks | Review and Evaluate Proposals (Technical Only) 4wks | Public Opening of Financial Proposals and Evaluation 2wks | Combine Technical and Financial Proposals 1 wks | Negotiation and Report Writing 2 wks | Approval of Negotiated contract Issues 2wks | Prepare Contract 2 wks | Approval Of Draft Contract 2 wks | Sign Contract / Advance Payment 4 wks | Contract Period 4- 52 wks
1 | Printing and Publications of Manuals | MFMR/ADMIN/SERV/NCB/01/2021 | 378500000 | NCB | Plan | 2020-12-02 | 2020-12-30 | 2021-01-06 | 2020-01-20 | 2021-02-03 | 2021-03-03 | 2021-03-31 | 2021-04-14 | 2021-04-21 | 2021-05-05 | 2021-05-19 | 2021-06-02 | 2021-06-16 | 2021-07-14 | 2021-08-11
Actual
2 | Maintainance of PB SIK (Boat) | MFMR/MCS/SERV/NCB/02/2021 | 500000000 | NCB | Plan | 2021-11-30 | 2021-12-28 | 2021-01-04 | 2021-01-18 | 2021-02-01 | 2021-03-01 | 2021-03-29 | 2021-04-12 | 2021-04-19 | 2021-05-03 | 2021-05-17 | 2021-05-31 | 2021-06-14 | 2021-07-12 | 2021-08-09
Actual
3 | Maintenance of Air Conditioners | MFMR/ADMIN/SERV/RFQ/01/2021 | 6500000 | RFQ | Plan | 2021-11-02 | 2020-11-30 | 2020-12-07 | 2020-12-21 | 2021-01-04 | 2021-02-01 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-17 | 2021-06-14 | 2021-07-12
Actual
4 | Maintenance of Fish Ponds and CLEANING TOOLS: | MFMR/FQ/SERV/NCB/03/2021 | 295825000 | NCB | Plan | 2020-11-09 | 2020-12-07 | 2020-12-14 | 2020-12-28 | 2021-01-11 | 2021-02-08 | 2021-03-04 | 2021-03-18 | 2021-03-25 | 2021-04-08 | 2021-04-22 | 2021-05-06 | 2021-05-20 | 2021-06-17 | 2021-07-15
Actual
5 | Catering Services (Food and Drinks) | MFMR/ADMIN/SERV/NCB/04/2021 | 1016755000 | NCB | Plan | 2020-11-04 | 2020-12-02 | 2020-12-09 | 2020-12-23 | 2021-01-06 | 2021-02-03 | 2021-03-03 | 2021-03-17 | 2021-03-24 | 2021-04-07 | 2021-04-21 | 2021-05-05 | 2021-05-19 | 2021-06-16 | 2021-07-14
Actual
6 | Vehicle Maintenance and Hire | MFMR/ADMIN/SERV/NCB/05/2021 | 829360000 | NCB | Plan | 2020-10-26 | 2020-11-23 | 2020-11-30 | 2020-12-14 | 2020-12-28 | 2021-01-25 | 2021-02-22 | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-04-12 | 2021-04-26 | 2021-05-10 | 2021-06-07 | 2021-07-05
Actual
7 | Consultancy fees (SAMPLING PROCEDURES FOR FISHERIES PRODUCTS FRESHNESS AND CONTAMINATION) | MFMR/STAT/SERV/NCB/06/2021 | 125000000 | NCB | Plan | 2020-10-19 | 2020-11-16 | 2020-11-23 | 2020-12-07 | 2020-12-21 | 2021-01-18 | 2021-02-15 | 2021-03-01 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-31 | 2021-05-28
Actual
8 | Review of the Fish and Fisheries Product Regulations 2007 for the Competent Authority | MFMR/ADMIN/SERV/NCB/07/2021 | 300000000 | NCB | Plan | 2020-11-25 | 2020-12-23 | 2020-12-30 | 2021-01-13 | 2021-01-27 | 2021-02-24 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-04-28 | 2021-05-12 | 2021-05-26 | 2021-06-09 | 2021-07-07 | 2021-08-04
Actual
9 | Management and upkeep of website | MFMR/ADMIN/SERV/NCB/08/2021 | 180000000 | NCB | Plan | 2020-10-05 | 2020-11-02 | 2020-11-09 | 2020-11-23 | 2020-12-07 | 2021-01-04 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-03-08 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-17 | 2021-06-14
Actual
10 | Brushing, Cleaning and pond management: | MFMR/ADMIN/SERV/NCB/09/2021 | 138600000 | NCB | Plan | 2020-10-20 | 2020-11-17 | 2020-11-24 | 2020-12-08 | 2020-12-22 | 2021-01-19 | 2021-02-16 | 2021-03-02 | 2021-03-09 | 2021-03-23 | 2021-04-06 | 2021-04-20 | 2021-05-04 | 2021-06-01 | 2021-06-29
Actual
11 | Repairs and maintenance of IPCs (Inshore Patrol Boats) | MFMR/ADMIN/SERV/NCB/10/2021 | 840000000 | NCB | Plan | 2020-11-09 | 2020-11-30 | 2020-12-07 | 2020-12-21 | 2021-01-04 | 2021-02-01 | 2021-03-01 | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-19 | 2021-05-03 | 2021-05-17 | 2021-06-14 | 2021-07-12
Actual
12 | Maintenance and repair of Office equipment | MFMR/ADMIN/SERV/RFQ/02/2021 | 15000000 | RFQ | Plan | 2020-12-02 | 2020-12-30 | 2021-01-06 | 2020-01-20 | 2021-02-03 | 2021-03-03 | 2021-03-31 | 2021-04-14 | 2021-04-21 | 2021-05-05 | 2021-05-19 | 2021-06-02 | 2021-06-16 | 2021-07-14 | 2021-08-11
| TOTAL |  | 4625540000 |  | Actual
Date of Approval by Procurement Committee…………...……………………………
Signature of Chairman, Procurement Committee…………………………………….
Prepared By: John Foray Lamin …………………………………

## Summary
MINISTRY OF FISHERIES AND MARINE RESOURCES | [8 empty] | Remarks
PROCUREMENT CATEGORY | Number of open types |  | Number of Restricted type (RFQ) | Values
| NCB | ICB |  | NCB( Le.) | ICB (Le.) | Restricted (RFQ) Le. | Total values of open type Le. | Total values of open and restricted type (RFQ) Le.
GOODS | 14 | 2 | 2 | 7897185000 | 11618259000 | 72600000 | 19515444000 | 19588044000
WORKS | 2 | NIL | 2 | 1737500000 |  | 320000000 | 1737500000 | 2057500000
SERVICES | 10 | NIL | 2 | 4610540000 |  | 21500000 | 4610540000 | 4632040000
TOTAL |  |  |  | 14245225000 | 11618259000 | 414100000 | 25863484000 | 26277584000
Summary of Procurement and Non-Procurement Items
Procurement Related Items | Total Restricted Bidding | 414100000
| Total Open Competitive Bidding | 25863484000
Sub Total |  | 26277584000
Non-Procurement Related Items |  | 9757151000
Non-Procurement Related Items
Total Operational Budget |  | 36034735000

## PDF & NPDF
MINISTRY OF FISHERIES AND MARINE RESOURCES
Disbursement Forecast For 2021 Budget
GOODS
Contract Package Number | Contract Description | Procurement Method | Contract Value Le | Payments To Date Le | Quarter 1 Jan - Mar Le | Quarter 2 Apr - Jun Le | Quarter 3 Jul - Sep Le | Quarter 4 Oct - Dec Le | Rollover Le
1 | Stationary | NCB | 420000000 | Nil | 105000000 | 105000000 | 105000000 | 105000000
2 | Computers and Accessories | NCB | 465500000 | Nil | 116375000 | 116375000 | 116375000 | 116375000
3 | Computer Consumable |  | 300000000 | Nil | 75000000 | 75000000 | 75000000 | 75000000
4 | Motor Bike and Number plates | NCB | 325000000 | Nil | 81250000 | 81250000 | 81250000 | 81250000
5 | Provisions and Sundries | NCB | 232000000 | Nil | 58000000 | 58000000 | 58000000 | 58000000
6 | Staff Uniforms; | NCB | 144000000 | Nil | 36000000 | 36000000 | 36000000 | 36000000
7 | Fuel and Lubricant | NCB | 5812540000 | Nil | 1453135000 | 1453135000 | 1453135000 | 1453135000
8 | Office funiture and Equipment | NCB | 786600000 | Nil | 196650000 | 196650000 | 196650000 | 196650000
9 | Purchase of raw materials in bags: | NCB | 301500000 | Nil | 75375000 | 75375000 | 75375000 | 75375000
10 | Running cost for JMC generator | NCB | 2600000 | Nil | 650000 | 650000 | 650000 | 650000
11 | Measuring guages | NCB | 221000000 | Nil | 55250000 | 55250000 | 55250000 | 55250000
12 | Procurement of laboratory tools and reagents | NCB | 550000000 | Nil | 137500000 | 137500000 | 137500000 | 137500000
13 | Assorted fishing net | NCB | 5805719000 | Nil | 1451429750 | 1451429750 | 1451429750 | 1451429750
14 | Procurement of the two fish feed machines | NCB | 345000000 | Nil | 86250000 | 86250000 | 86250000 | 86250000
15 | Outboard Engine (YAMAHA): | NCB | 1404000000 | Nil | 351000000 | 351000000 | 351000000 | 351000000
16 | Oil Paints, Paint brush and Thinner | RFQ | 70000000 | Nil | 17500000 | 17500000 | 17500000 | 17500000
17 | Fish, Safety and Rain Gears | NCB | 2204750000 | Nil | 551187500 | 551187500 | 551187500 | 551187500
18 | Tools for landing sites cleaning: | NCB | 197600000 | Nil | 49400000 | 49400000 | 49400000 | 49400000
|  |  | 19587809000 | Nil | 4896952250 | 4896952250 | 4896952250 | 4896952250
WORKS
1 | Rehabilitation of Kissy outstation building | NCB | 1500000000 | Nil | 375000000 | 375000000 | 375000000 | 375000000
2 | Extension of LAN Network Infrastructure; | NCB | 237500000 | Nil | 118750000 |  | 118750000
3 | Construction of standard 5-10 boats for experimental fishing | NCB | 150000000 | Nil | 75000000 | 75000000
4 | Building Maintenance; | NCB | 170000000 | Nil | 85000000 |  | 85000000
|  |  | 2057500000 | Nil | 653750000 | 450000000 | 578750000 | 375000000
SERVICES
1 | Maintainance of PB SIK | NCB | 500000000 | Nil | 125000000 | 125000000 | 125000000 | 125000000
2 | Maintenance of Air Conditioners | RFQ | 6500000 | Nil | 1625000 | 1625000 | 1625000 | 1625000
3 | Maintenance of Fish Ponds and CLEANING TOOLS: | NCB | 295825000 | Nil | 73956250 | 73956250 | 73956250 | 73956250
4 | Food and Drinks |  | 1016755000 | Nil | 254188750 | 254188750 | 254188750 | 254188750
5 | Vehicle Maintenance and Hire | NCB | 829360000 | Nil | 207340000 | 207340000 | 207340000 | 207340000
6 | Consultancy fees (SAMPLING PROCEDURES FOR FISHERIES PRODUCTS FRESHNESS AND CONTAMINATION) | NCB | 125000000 | Nil | 125000000 |  |  | 0
7 | Review of the Fish and Fisheries Product Regulations 2007 for the Competent Authority | NCB | 300000000 | Nil |  | 300000000
8 | Management and upkeep of website | NCB | 180000000 | Nil | 180000000
9 | Brushing, Cleaning and pond construction and management: | NCB | 138600000 | Nil |  | 138600000
10 | Printing | NCB | 378500000 | Nil | 94625000 | 94625000 | 94625000 | 94625000
11 | Repairs and maintenance of IPCs | NCB | 840000000 | Nil | 210000000 | 210000000 | 210000000 | 210000000
12 | Maintenance and repair of equipment | NCB | 15000000 | Nil | 15000000 |  |  | 0
|  |  | 4625540000 | Nil | 1286735000 | 1405335000 | 966735000 | 966735000
NON PROCUREMENT DISBURSEMENT FORECAST
1 | Media |  | 35030000 | Nil | 35030000
2 | Advertisements |  | 224000000 | Nil | 112000000 |  | 112000000
3 | Conducting inshore patrol with RHIB |  | 42000000 | Nil | 10500000 | 10500000 | 10500000 | 10500000
4 | DSA, Allowances and Tranports /refunds, Stripins and Sitting allowance(Local & International) |  | 5826159452.8 | Nil | 1456539863.2 | 1456539863.2 | 1456539863.2 | 1456539863.2
5 | Chair Rentals |  | 4100000 | Nil | 4100000
6 | subsrcrition for AIS software EXACT EARTH |  | 57000000 | Nil | 57000000
7 | Subscription for PSMA electronic information exchange platform |  | 12000000 | Nil | 12000000
8 | Fees for laboratory tests |  | 600000000 | Nil | 600000000
9 | Training and capacity building materials (Local & International) |  | 350725000 | Nil |  | 350725000
10 | Flight (Ticket) |  | 177509500 | Nil | 88754750 |  | 88754750
11 | Top-Up Cards |  | 38000000 | Nil | 9500000 | 9500000 | 9500000 | 9500000
12 | Electricity; |  | 100000000 | Nil | 25000000 | 25000000 | 25000000 | 25000000
13 | Water; |  | 60000000 | Nil | 15000000 | 15000000 | 15000000 | 15000000
14 | Licence and Insurance - Motor Vehicles & Bikes; |  | 12525000 | Nil | 12525000
15 | Average Monthly Imprest |  | 150000000 | Nil | 37500000 | 37500000 | 37500000 | 37500000
16 | Venue booking and facilitation for training and outdoor meetings |  | 30000000 | Nil | 7500000 | 7500000 | 7500000 | 7500000
17 | Data Entry Clerk , M&E and data validation (ENVIRONMENTAL MONITORING PLAN AND SAMPLING PROCEDURES FOR FISHERIES PRODUCTS FRESHNESS AND CONTAMINATION |  | 100000000 | Nil | 25000000 | 25000000 | 25000000 | 25000000
OUTSTANDING PAYMENT (Roll Over Activities)
1 | Procurement of VHF and HF radio |  | 79109713.2 |  | 79109713.2
2 | Six (6) fiber glass boat |  | 1361679384 |  | 1361679384
3 | Procurement of 2500 life jackets |  | 103366350 |  | 103366350
4 | Construction of outstation of at Sulima |  | 393946600 |  | 393946600
|  |  | 9757151000 |  | 4446051660.4 | 1937264863.2 | 1787294613.2 | 1586539863.2
|  | TOTAL | 36028000000 |  | 11283488910.4 | 8689552113.2 | 8229731863.2 | 7825227113.2

## Agreegation
MINISTRY OF FISHERIES AND MARINE RESOURCES
AGGREGATION-2021
| SUB-DEPARTMENT | Assorted Stationery | Sundries | Imprest | Office funiture and Equipment | Management and upkeep of website | Running cost for JMC generator | Chair Rentals | subsrcrition for AIS software EXACT EARTH | Subscription for PSMA electronic information exchange platform | Conducting inshore patrol with RHIB | Fees for laboratory tests | Measuring guages | Data Entry Clerk , M&E and data validation | Computers and Accessories | Motor Bike and Accessories | Fuel and Lubricant | Top-Up Cards | Electricity; | Building Maintenance; | Water; | Licence and Insurance - Motor Vehicles & Bikes; | Uniforms; | Machinery & Equip’t Maintenance; | Printing | Venue booking and facilitation for training and outdoor meetings | Procurement of laboratory tools and reagents | Consultancy fees | Procurement of VHF and HF radio | Assorted fishing net | Six (6) fiber glass boat | Construction | Advertisements | Review of the Fish and Fisheries Product Regulations 2007 for the Competent Authority | Construction of outstation of at Sulima | Purchase of raw materials in bags: | Brushing, Cleaning and pond construction and management: | Procurement of the two fish feed machines | Rehabilitation of Kissy outstation building | Extension of LAN Network Infrastructure; | Outboard Engine (YAMAHA): | Fish, Safety and Rain Gears | Tools for landing sites cleaning: | Food and Drinks | Maintenance of Air Conditioners | Procurement of 2500 life jackets | Maintenance of Fish Ponds and CLEANING TOOLS: | Vehicle Maintenanceand Hire | Construction of standard 5-10 boats for experimental fishing | DSA, Allowances and Tranports /refunds, Stripins and Sitting allowance(Local & International) | Training and capacity building materials (Local & International) | Flight Tickets | Media | TOTAL
|  | (Le) | (Le) |  | (Le) | (Le) | [8 empty] | (Le) | (Le) | (Le) | (Le) | [7 empty] | (Le) | (Le) | [13 empty] | (Le) | (Le) | (Le) | (Le) | (Le) |  | (Le) | (Le) | (Le) | (Le) |  | (Le) | (Le) | (Le)
1 | Administration | 636000000 | 232000000 | 150000000 | 306000000 | [11 empty] | 915600000 |  | 100000000 | 170000000 | 60000000 | 12525000 | 144000000 | 15000000 | 22500000 |  |  |  | 79109713.2 | 2805719000 | 1361679384 |  |  | 300000000 | 393946600 |  |  |  | 1500000000 |  |  |  |  | 38160000 |  | 103366350 |  | 825360000 |  | 793406113.2 | 110725000 | 177509500 |  | 11252606660.4
Actual
2 | Support to Various Administrative Unit |  |  |  |  | 180000000 | [10 empty] | 162750000 | [7 empty] | 120000000 | [7 empty] | 204000000 | [6 empty] | 237500000 |  |  |  | 14400000 | [5 empty] | 513900000 |  |  |  | 1432550000
Actual
3 | Fish Quality and Processing Unit | [6 empty] | 700000 | [8 empty] | 42000000 | [9 empty] | 550000000 | [16 empty] | 46855000 | [5 empty] | 509100000 |  |  |  | 1148655000
Actual
3 | Marine Artisanal Fisheries Unit | 41000000 |  |  | 313400000 |  |  |  | 57000000 | 12000000 | 42000000 | 600000000 |  | 10000000 |  | 325000000 | 371600000 | 38000000 | [6 empty] | 61000000 |  |  |  |  | 3000000000 | [10 empty] | 1404000000 | 2001500000 | 197600000 | 50000000 |  |  |  |  | 150000000 | 1541702226.4 |  |  | 35030000 | 10250832226.4
Actual
4 | Aquaculture and Inland Fishing Unit |  |  |  | 1100000 | [7 empty] | 27000000 |  | 36000000 |  | 33600000 | [7 empty] | 30000000 |  |  | 80000000 |  |  |  | 550000000 | 20000000 |  |  | 301500000 | 138600000 | 345000000 |  |  |  | 81000000 |  | 24000000 |  |  | 247075000 |  |  | 349400000 |  |  |  | 2264275000
Actual
5 | Monitoring, Control and Surveilance Unit | 20000000 |  |  | 79600000 |  | 2600000 | [5 empty] | 24000000 |  | 119500000 |  | 4162990000 | [24 empty] | 11250000 |  | 392800000 | 6500000 |  |  |  |  | 669000000 |  |  |  | 5488240000
Actual
6 | Policy, Planning, Research and Statistics Unit | 18000000 |  |  | 66500000 | [7 empty] | 170000000 |  | 310000000 |  | 75000000 | [7 empty] | 130000000 | 30000000 | [15 empty] | 87500000 |  | 107100000 | [5 empty] | 904551113.2 | 240000000 |  |  | 2138651113.2
Actual
7 | Competent Authority | 5000000 | [5 empty] | 3400000 | [5 empty] | 90000000 |  |  | 49000000 | [7 empty] | 15000000 |  |  | 925000000 | [13 empty] | 23500000 |  | 343440000 |  |  | 48750000 | 4000000 |  | 545100000 |  |  |  | 2052190000
Actual
| 50% adjusted | 702000000 | 232000000 | 150000000 | 766600000 | 180000000 | 2600000 | 4100000 | 57000000 | 12000000 | 42000000 | 600000000 | 221000000 | 100000000 | 465500000 | 325000000 | 5812540000 | 38000000 | 100000000 | 170000000 | 60000000 | 12525000 | 144000000 | 15000000 | 378500000 | 30000000 | 550000000 | 1005000000 | 79109713.2 | 5805719000 | 1361679384 | 550000000 | 224000000 | 300000000 | 393946600 | 301500000 | 138600000 | 345000000 | 1500000000 | 237500000 | 1404000000 | 2204750000 | 197600000 | 1016755000 | 6500000 | 103366350 | 295825000 | 829360000 | 150000000 | 5826159452.8 | 350725000 | 177509500 | 35030000 | 36028000000
| PROCUREMENT METHOD | NCB | NCB |  | NCB | NCB | RFQ | RFQ |  |  |  |  | NCB | NCB | NCB | NCB | NCB | RFQ | NPDF | RFQ | RFQ | ND | NCB | RFQ | NCB | NPDF | NCB | NCB |  | ICB | ICB | NCB | NDPF | NCB | NPDF | NCB | NCB | NCB | NCB | NCB | NCB | NCB | NCB | NCB | RFQ | NDPF | NCB | NCB | NCB | NPDP | NCB | NCB | NPDF | 36028000000

## Cover Page
MINISTRY OF FISHERIES AND MARINE RESOURCES
PROCUREMENT PLAN 2021