## Cover
MINISTRY OF WORKS AND PUBLIC ASSET
PROCUREMENT PLAN 2021 FY
PREPARED BY THE PROCUREMENT UNIT
APPROVED BY THE PROCUREMENT COMMITTEE

## Goods
Ministry of Works and Public Assets
Name of Sub-Department - Finance and Admin |  | Proffessional & Administrative Wings | [10 empty] | Procurement Plan 2019
Source of Funding-GOSL | [13 empty] | Goods
Serial | Description of Contract | Procurement | Lot No | Estimated | Proc. | Plan/Actual | Submission by Procurement Unit | Date of Clearance by Committee | Choice of Newspapers for advert publication | Bid Invitation | Bid Closing/ | Submission of | Approved by | Date of Notification of | Date of Sign | Est. Letter | Delivery | Insp/Final | Remarks
Ministry of Works and Public Assets
Name of Sub-Department - Finance and Admin |  | Proffessional & Administrative Wings | [10 empty] | Procurement Plan 2019
Source of Funding-GOSL | [13 empty] | Goods
Serial | Description of Contract | Procurement | Lot No | Estimated | Proc. | Plan/Actual | Submission by Procurement Unit | Date of Clearance by Committee | Choice of Newspapers for advert publication | Bid Invitation | Bid Closing/ | Submission of | Approved by | Date of Notification of | Date of Sign | Est. Letter | Delivery | Insp/Final | Remarks
No |  | No. |  | Cost | Method | Date | Procurement Unit |  |  | Date | Opening Date | Evaluation | Procurement | Contract | Contract | of Credit adv. | Period | Acceptance
[12 empty] | Report | Committee | Award |  | P/ment
1 | Procurement of Stores and Office Supplies | MWPA/G/NCB/001/2020 |  | 352000000 | NCB | Plan | 2020-09-04 | 2020-09-17 | 2020-09-18 | 2020-09-21 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-23 | 2020-12-01 | 2021-01-18 | 2021-01-25 | Framework Contract
Actual
2 | Procurement of Stationery | MWPA/G/NCB/002/2020 |  | 167638000 | NCB | Plan | 2020-09-10 | 2020-09-24 | 2020-09-25 | 2020-09-28 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-27 | 2020-12-28 | 2021-01-08 | 2021-08-16 | Framework Contract
Actual
3 | Computer Consumables | MWPA/G/NCB/003/2020 |  | 273549910 | NCB | Plan | 2020-09-11 | 2020-09-25 | 2020-09-28 | 2020-10-01 | 2020-10-29 | 2020-11-05 | 2020-11-12 | 2020-11-19 | 2020-12-09 | 2020-12-31 | 2021-01-14 | 2021-01-21 | Framework Contract
Actual
4 | Procurement of Office Equipment | MWPA/G/NCB/004/2020 |  | 228618100 | NCB | Plan | 2020-09-17 | 2020-10-01 | 2020-10-01 | 2020-10-02 | 2020-11-02 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-12-08 | 2021-01-03 | 2021-01-18 | 2021-01-22
Actual
5 | Procurement of Ofifice Furniture | MWPA/G/NCB/005/2020 |  | 78000000 | RFQ | Plan | 2020-10-15 | 2020-10-22 | NA | 2020-10-23 | 2020-11-06 | 2020-11-13 | 2020-11-18 | 2020-11-23 | 2019-11-27 | N/A | 2021-12-01 | 2021-12-18
Actual
6 | Procurement of Uniforms & Protective Clothing | MWPA/G/RFQ/006/2020 |  | 16250000 | RFQ | Plan | 2021-08-30 | 2021-09-03 | NA | 2021-09-06 | 2021-09-20 | 2021-09-24 | 2021-10-01 | 2021-10-08 | 1015/2021 | N/A | 2021-10-18 | 2021-10-20
Actual
7 | Procurement of Survey & Engineering Tools | MWPA/G/NCB/007/2020 |  |  | NCB | Plan | 2020-09-25 | 2020-10-16 | 2020-10-23 | 2020-10-26 | 2020-11-27 | 2020-12-04 | 2020-12-07 | 2020-12-08 | 2020-12-23 | 2021-01-25 | 2021-02-08 | 2021-02-15
Actual
8 | Procurement of Spare Parts | MWPA/G/NCB/008/2020 |  | 177170000 | NCB | Plan | 2020-10-16 | 2020-10-29 | 2020-10-30 | 2020-11-02 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2021-01-04 | 2021-01-29 | 2021-02-15 | 2021-02-22 | Framework Contract
Actual
9 | Procurement of Bikes | MWPA/G/RFQ/009/2020 |  |  | NCB | Plan | 2020-10-12 | 2020-10-26 | 2020-10-29 | 2020-10-30 | 2020-11-27 | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2021-01-08 | 2021-01-29 | 2021-02-12 | 2021-02-19
Actual
10 | Procurement of Technical instrument and trespassers warning sign posts: | MWPA/G/RFQ/010/2020 |  | 315900000 | NCB | Plan | 2020-10-12 | 2020-10-26 | 2020-10-29 | 2020-10-30 | 2020-11-27 | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2021-01-08 | 2021-01-29 | 2021-02-12 | 2021-02-19
Actual
11 | Procurement of Vehicles & EQPT | MWPA/G/RFQ/011/2020 |  | 2479000000 | ICB | Plan | 2020-10-30 | 2020-11-12 | 2020-11-13 | 2020-11-16 | 2020-12-28 | 2021-01-11 | 2021-01-25 | 2021-02-08 | 2021-02-26 | 2021-03-22 | 2021-06-21 | 2021-06-28
Actual
12 | Service Charter and Bill Boards | MWPA/G/RFQ/012/2020 |  |  | RFQ | Plan | 2020-10-15 | 2020-10-22 | NA | 2020-10-23 | 2020-11-06 | 2020-11-13 | 2020-11-18 | 2020-11-23 | 2021-11-27 | N/A | 2021-12-11 | 2021-12-18
Actual
14 | Computer assessories | MWPA/G/RFQ/014/2020 |  | 49357500 | RFQ | Plan | 2020-12-11 | 2020-12-18 | NA | 2020-12-21 | 2020-12-28 | 2021-01-03 | 2021-01-04 | 2021-01-07 | 2021-01-11 | N/A | 2021-01-14 | 2021-01-14
Actual
| TOTAL |  |  | 4137483510
| Senior Procurement Officer ……………………………………………. | [10 empty] | Chairman Procurement Committee …………………………………………..
| Messie Kemokai ( mrs) | [11 empty] | Rukiatu K. Kamara(Mrs.)

## Works
| Name of Procuring Entity: | MINISTRY OF WORKS AND PUBLIC ASSETS
| Name of Sub-Department: | Proffessional & Administrative Wings
| Source of funding: | GOSL
[8 empty] | Review of documents | Bidding period |  | Bid Evaluation |  |  |  | Contract Implementation
Serial | Description of works | procurement number | Lot | Estimated cost in Leones | Pro. Meth. | Plan Vs Actual Dates | Information & bid documents | Date of clearance Committee | Bid Invitation | Bid Closing | Submission report | Approved by procurement | Notification Date of contract | Date of Contract Signature | Initial Payment | Commencement | Completion of Contract | Defect Liability | Inspection & Final Acceptance
1 | Management of Coastal Erosion and Seaface Protection | MWPA/W/NCB/001/2020 |  | 407250000 | NCB | Plan | 2020-10-06 | 10/12//2020 | 10/16//2020 | 11/13//2020 | 11/20//2020 | 12/3//2020 | 12/4//2020 | 12/18//2020 | 2021-01-04 | 2021-01-11 | 2021-03-08 | 2021-06-07 | 2021-06-21
Actual
2 | Maintenance of access roads to Government Properties | MWPA/W/NCB/002/2020 |  | 1160000000 | ICB | Plan | 10/6//2020 | 10/13//2020 | 10/16//2020 | 11/27//2020 | 12/1//2020 | 12/3//2020 | 12/4//2020 | 12/18//2020 | 2021-01-04 | 2021-01-14 | 2021-03-12 | 2021-06-10 | 2021-06-28
Actual
3 | Maintenance & Repairs of Government Quarters | MWPA/W/1CB/003/2020 |  | 5007400000 | ICB | Plan | 10/6//2020 | 10/13//2020 | 10/19//2020 | 11/30//2020 | 12/3//2020 | 12/7//2020 | 12/8//2020 | 12/22//2020 | 2021-01-06 | 2021-01-18 | 2021-03-12 | 6//142021 | 2021-06-30
Actual
| TOTAL |  |  | 6574650000
| Prepared by……………………………………………….. | [8 empty] | Date of Approval by Chairman Procurement Committee ………………………………… | [8 empty] | 2019
Messie Kemokai ( mrs)
| Senior Procurement Officer | [8 empty] | Signed by Chairman Procurement Committee …………………………………………….
Rukiatu K. Kamara(Mrs.)

## Services
SERVICES
| Name of Procuring Entity: |  | Ministry of Works and Public Asset
| Name of Sub-Department: |  | Proffessional & Administrative Wings
| Source of funding: |  | GOSL
|  |  | BASIC DATA |  |  |  |  | Expressions of Interest |  |  | TOR/RFP Preparation |  | Consultants' Proposals | Consultants' Proposals |  | Proposal Evaluation(Technical and Financial) |  |  |  |  | Negotiations |  |  | Contract Finalisation |  |  | Contract Implementation
| Description of Services | procurement number | estimated cost. Le | estimated cost.USD | selection method | plan vs actual dates | EOI invited | Shortlist | Date of clearance by Procurement Committee | Preparation of TOR | Preparation of RFP | Date of approval by Procurement Committee | Invitation Date | Submission Date/Opening | Submission of Evaluation Report (T) | Approval of Evaluation Report(T) | Opening of Financial Proposal | Submission of combined evaluation report(T&F) | Approval of Evaluation Report(T&F) | Negotiations | Draft Contract | Approval of Negotiation Report | Contract Amount | Date of Award | Date of Contract signature | Mobilisation/ Advance payment | Inception report | Draft report | Final report | Final cost
Vote Code
1 | Security services to MWPA & Youyi Building | MWPA/S/ICB/001/2020 | 1132800000 |  | ICB | Plan | 2020-09-07 | 2020-10-16 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-16 | 2020-11-17 | 2020-12-18 | 2020-12-23 | 2020-12-28 | 2021-01-11 | 2021-01-18 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-03-02 | N/A | 2021-03-08 | 2021-03-22 | 2021-04-12 |  | N/A | Quarterly | N/A
Actual
2 | Cleaning services to MWPA & Youyi Building | MWPA/S/ICB/002/2020 | 876000000 |  | ICB | Plan | 2020-09-07 | 2020-10-16 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-16 | 2020-11-17 | 2020-12-18 | 2020-12-23 | 2020-12-28 | 2021-01-11 | 2021-01-18 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-03-02 | N/A | 2021-03-08 | 2021-03-22 | 2021-04-12 |  | N/A | Quarterly | N/A
Actual
3 | Machinery & Equipment Maintenance | MWPA/S/NCB/003/2020 | 445600000 |  | NCB | Plan | NA | NA | NA | NA | 2020-09-18 | 2020-10-02 | 2020-10-05 | 2020-10-30 | 2020-11-05 | 2020-11-09 | 2020-11-13 | 2020-11-18 | 2020-11-30 | 2020-12-14 | 2020-12-21 | 2020-12-28 | N/A | 2021-01-04 | 2021-01-11 | 2021-02-01 |  | N/A | 2021-02-08 | N/A
Actual
4 | Routine Maintenece at Youyi Building and Miatta Conference Centre | MWPA/S/NCB/004/2020 | 60000000 |  | RFQ | Plan | NA | NA | NA | NA | 2020-11-02 | 2020-11-09 | 2020-11-13 | 2020-11-27 | NA | NA | NA | 2020-12-04 | 2020-12-18 | NA | NA | NA | N/A | 2020-12-28 | 2021-01-12 | NA | NA | NA | 2021-01-25 | N/A
Actual
5 | Maintenance of Generator | MWPA/S/RFQ/005/2020 | 68000000 |  | RFQ | Plan | NA | NA | NA | NA | 2020-11-02 | 2020-11-09 | 2020-11-13 | 2020-11-27 | NA | NA | NA | 2020-12-04 | 2020-12-18 | NA | NA | NA | N/A | 2020-12-28 | 2021-01-12 | NA | NA | NA | 2021-01-25 | N/A
Actual
6 | Coding of Assets | MWPA/S/RFQ/006/2020 | 30000000 |  | RFQ | Plan | NA | NA | NA | NA | 2020-11-02 | 2020-11-09 | 2020-11-13 | 2020-11-27 | NA | NA | NA | 2020-12-04 | 2020-12-18 | NA | NA | NA | N/A | 2020-12-28 | 2021-01-12 | NA | NA | NA | 2021-01-25 | N/A
Actual
| Printing | MWPA/S/RFQ/007/2020 | 134000000 |  | NCB | Plan | NA | NA | NA | NA | 2020-09-18 | 2020-10-02 | 2020-10-05 | 2020-10-30 | 2020-11-05 | 2020-11-09 | 2020-11-13 | 2020-11-18 | 2020-11-30 | 2020-12-14 | 2020-12-21 | 2020-12-28 | N/A | 2021-01-04 | 2021-01-11 | 2021-02-01 |  | N/A | 2021-02-08 | N/A
Actual
| vehicle Hiring | MWPA/S/RFQ/008/2020 | 1025600000 |  | ICB | Plan | 2020-09-07 | 2020-10-16 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-16 | 2020-11-17 | 2020-12-18 | 2020-12-23 | 2020-12-28 | 2021-01-11 | 2021-01-18 | 2021-02-01 | 2021-02-15 | 2021-02-22 | 2021-03-02 | N/A | 2021-03-08 | 2021-03-22 | 2021-04-12 |  | N/A | Quarterly | N/A
Actual
TOTAL
Messie Kemokai ( mrs) | [6 empty] | ……………………………………………………….
Senior Procurement Officer ………………. |  |  |  |  | Chairman Procurement Committee |  |  | …………………………….
Rukiatu K. Kamara(Mrs.)

## PDF
MINISTRY OF WORKS AND PUBLIC ASSETS
PROCUREMENT ACTIVITIES FORECAST 2019 BUDGET
CONTRACT PACKAGE NO. | CONTRACT DESCRIPTION | PROCUREMENT METHOD | CONTRACT VALUE | PAYMENT TO DATE | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4
[5 empty] | JAN-MARCH | APRIL-JUNE | JULY- SEPT | OCT- DEC
GOODS
1 | Stores and Office Supplies | NCB | 352000000 |  | 88000000 | 88000001 | 88000002 | 88000003
2 | Stationery | NCB | 167638000 |  | 41909500 | 41909500 | 41909500 | 41909500
3 | Computer Consumables | NCB | 273549910 |  | 68387477.5 | 68387477.5 | 68387477.5 | 68387477.5
4 | Office Equipments | NCB | 228618100 |  | 57154525 | 57154525 | 57154525 | 57154525
5 | Office Furniture | RFQ | 78000000 |  | 19500000 | 19500000 | 19500000 | 19500000
6 | Uniforms & Protective Clothing | RFQ | 16250000 |  | 4062500 | 4062500 | 4062500 | 4062500
7 | Survey & Engineering Tools | NCB
8 | Procurement of Spare Parts | NCB | 177170000 |  | 44292500 | 44292500 | 44292500 | 44292500
9 | Procurement of Bikes | NCB
10 | Procurement of Technical instrument and trespassers warning sign posts: | NCB | 315900000 |  | 78975000 | 78975000 | 78975000 | 78975000
11 | Procurement of Vehicles | ICB | 2479000000 |  | 619750000 | 619750000 | 619750000 | 619750000
12 | Computer assessories | RFQ | 49357500 |  | 12339375 | 12339375 | 12339375 | 12339375
13 | Service Charter & Bill Boards | RFQ
| Sub Total |  | 4137483510 |  | 1034370877.5 | 1034370878.5 | 1034370879.5 | 1034370880.5
WORKS
1 | Management of Coastal Erosion and Seaface Protection | NCB | 407250000 |  | 101812500 | 101812500 | 101812500 | 101812500
2 | Maintenance of access roads to Government Properties | ICB | 1160000000 |  | 290000000 | 290000000 | 290000000 | 290000000
3 | Maintenance & Repairs of Government Quarters |  | 5007400000 |  | 1251850000 | 1251850000 | 1251850000 | 1251850000
|  | Sub Total | 6574650000 |  | 1643662500 | 1643662500 | 1643662500 | 1643662500
SERVICES
1 | Security Services | ICB | 1132800000 |  | 283200000 | 283200000 | 283200000 | 283200000
2 | Cleaning & Fumigation | ICB | 876000000 |  | 219000000 | 219000000 | 219000000 | 219000000
3 | Routine Maintenece at Youyi Building and Miatta Conference Centre | RFQ | 60000000 |  | 15000000 | 15000000 | 15000000 | 15000000
4 | Machinery & Equipment Maintenance | NCB | 445600000 |  | 111400000 | 111400000 | 111400000 | 111400000
5 | Printing | NCB | 134000000 |  | 33500000 | 33500000 | 33500000 | 33500000
6 | vehicle Hiring | ICB | 1025600000 |  | 256400000 | 256400000 | 256400000 | 256400000
7 | Maintenance of Generator | RFQ | 68000000 |  | 17000000 | 17000000 | 17000000 | 17000000
8 | Coding of Assets | RFQ | 30000000 |  | 7500000 | 7500000 | 7500000 | 7500000
|  | Sub Total | 3772000000 |  | 943000000 | 943000000 | 943000000 | 943000000
34246700000
| TOTAL PDF |  | 14484133510
Prepared by………………………………. |  |  |  |  | Date of Approval by Procurement Chairman……………………
Messie Kemokai ( mrs)
SENIOR PROCUREMENT OFFICER
Signature: Chairman Procument Committee……………………
Rukiatu K. Kamara(Mrs.)

## NPDF
0
MINISTRY OF WORKS AND PUBLIC ASSETS
NON PROCUREMENT ACTIVITIES FORECAST 2019 BUDGET
CONTRACT PACKAGE NO. | CONTRACT DESCRIPTION | PROCUREMENT METHOD | CONTRACT VALUE | PAYMENT TO DATE | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4
[5 empty] | JAN-MARCH | APRIL-JUNE | JULY- SEPT | OCT- DEC
1 | Basic Salaries for Staff | N/A | [6 empty] | 0
| Regulation of Petroleum Storage Facilities |  | 466750000 |  | 116687500 | 116687500 | 116687500 | 116687500 | 0
1 | Electricity | NA | 880000000 |  | 220000000 | 220000000 | 220000000 | 220000000
2 | Water | NA | 290000000 |  | 72500000 | 72500000 | 72500000 | 72500000
3 | Imprest | NA | 540000000 |  | 135000000 | 135000000 | 135000000 | 135000000
4 | Advertisement | N/A | 20000000 |  | 5000000 | 5000000 | 5000000 | 5000000
5 | DSTV Installation & Subscription | N/A
| Quarterly Monitoring and Inspection of Public Buildings and other Infrastructure Nationwide |  | 434384000 |  | 108596000 | 108596000 | 108596000 | 108596000
| Quarterly Monitoring and Evaluation of Rehabilitation Works to Trunk and Feeder Roads Nationwide |  | 434384000 |  | 108596000 | 108596000 | 108596000 | 108596000
6 | Hosting of Website | N/A | 122400000 |  | 30600000 | 30600000 | 30600000 | 30600000
7 | DSA | N/A | 137073500 |  | 34268375 | 34268375 | 34268375 | 34268375
8 | Workshops | N/A
9 | Radio & T.V Discussions | N/A | 12000000 |  | 3000000 | 3000000 | 3000000 | 3000000
10 | Newspapers | N/A | 63400000 |  | 15850000 | 15850000 | 15850000 | 15850000
12 | Overseas Training | N/A | 29561250 |  | 7390312.5 | 7390312.5 | 7390312.5 | 7390312.5
13 | Local Training | N/A | 105000000 |  | 26250000 | 26250000 | 26250000 | 26250000
| Structural Integrity test on public infrastructure: |  | 245392000 |  | 61348000 | 61348000 | 61348000 | 61348000
1 | Payment , insurance & valuation of Govt. rented Ofices | N/A
2 | Insurance for Vehicles & Bikes | N/A | 3000000 |  | 750000 | 750000 | 750000 | 750000
| Cadastral Survey of Government Property: | N/A | 70274000 |  | 17568500 | 17568500 | 17568500 | 17568500
3 | Internal Audit Activities | N/A | 319000000 |  | 79750000 | 79750000 | 79750000 | 79750000
| Inspection and Verification of Contractors Offices and Works yards by the Contractors Registration Board: |  | 240788000 |  | 60197000 | 60197000 | 60197000 | 60197000
| Rent & Rate |  | 13000000000 |  | 3250000000 | 3250000000 | 3250000000 | 3250000000
| Licence fee for Iphone |  | 6000000 |  | 1500000 | 1500000 | 1500000 | 1500000
| Verification of Government rented Properties Nationwide: |  | 28440000 |  | 7110000 | 7110000 | 7110000 | 7110000
| Inspection of work site |  | 197344000 |  | 49336000 | 49336000 | 49336000 | 49336000
| Service Contract |  | 120000000 |  | 30000000 | 30000000 | 30000000 | 30000000
| Subvention to Sierra Leone Institute of Engineers |  | 80000000 |  | 20000000 | 20000000 | 20000000 | 20000000
| Hospitality for Meetings |  | 50000000 |  | 12500000 | 12500000 | 12500000 | 12500000
| Fuel |  | 1050381740 |  | 262595435 | 262595435 | 262595435 | 262595435
| Budget Formulation ,Execution and Monitoring |  | 75100000 |  | 18775000 | 18775000 | 18775000 | 18775000
| Retreat for the Ministry |  | 500000000 |  | 125000000 | 125000000 | 125000000 | 125000000
| Overseas Traveling |  | 141894000 |  | 35473500 | 35473500 | 35473500 | 35473500
| Local Traveling |  | 80000000 |  | 20000000 | 20000000 | 20000000 | 20000000
| Facilation fee for the PRO Office |  | 20000000 |  | 5000000 | 5000000 | 5000000 | 5000000
| SUB TOTAL |  | 19762566490 |  | 4940641622.5 | 4940641622.5 | 4940641622.5 | 4940641622.5 |  | 14484133510
TOTAL PDF/NPDF
Prepared by………………………………. |  |  |  |  | Date of Approval by Procurement Chairman……………………
Messie Kemokai ( mrs)
Senior Procurement Officer
Signature: Chairman Procument Committee……………………
Rukiatu K. Kamara(Mrs.)

## Corrected Summary
Ministry of Works and Public Assets
SUMMARY OF MINISTRY OF WORKS AND PUBLIC ASSETS PROCUREMENT PLAN 2019
PROCUREMENT CATEGORY | TYPE OF CONTRACTS
| Number of restricted Bidding | NUMBER OF OPEN COMPETITIVE BIDDING |  | VALUES (Le.) |  |  | Total value of open and restricted Bidding (Le) | Remarks
|  | NCB | ICB | Total restricted Bidding(Le) | NCB | ICB
GOODS | 3 | 6 | 1 | 143607500 | 1514876010 | 2479000000 | 3993876010
WORKS | 0 | 1 | 2 |  | 407250000 | 6167400000 | 6574650000
SERVICES | 3 | 2 | 3 | 158000000 | 579600000 | 3034400000 | 3614000000
GRAND TOTAL | 6 | 9 | 6 | 301607500 | 2501726010 | 11680800000 | 14182526010
Summary of Procurement and Non-Procurement Items
Procurement Related Items | Total Restricted Bidding | 301607500
| Total Open Competitive Bidding | 14182526010
Sub Total
Non-Procurement Related Items |  | 19762566490
Total Operational Budget |  | 34246700000